## Sheet1
RiskID | Risk | Probability Description | Probability | Effect Description | Effect | Our Plan
R1 | The time required to develop the software is underestimated | High | 8 | Serious | 8 | Reschedule the whole project, hire more developers or divide the project by phases
R2 | Cloud service is unavailable or underperformance | Moderate | 4 | Serious | 8 | Look for another cloud service
R3 | API service is unavailable | Moderate | 6 | Tolerable | 6 | Price Comparison function may need to disable until the API service is resumed
R4 | Change in management (requiring fewer developers) | Low | 2 | Tolerable | 5 | Reallocated tasks of the developers
R5 | Lack of developers due to virus outbreak | Moderate | 6 | Serious | 8 | May need to reschedule the whole project
R6 | Client changes all the requirement | Moderate | 5 | Serious | 9 | May need to seize the project and plan a new one
R7 | Scope of projects on payment gateway integration is underestimated | High | 7 | Tolerable | 7 | Hire payment gateway experts
R8 | Software tools no longer supported | Low | 3 | Tolerable | 6 | Search new software tools
R9 | Legal issues on copyrights (e.g. on product images) | Moderate | 4 | Tolerable | 4 | Take the project images by ourselves
Note on D1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-10