## Sheet1
Task No | Task Name
T1 | Site Wireframes
T2 | Product List & Details
T3 | Customer Portal
T4 | Shopping Cart
T5 | Price Comparison
T6 | Order Status Tracking
T7 | UI/UX Enhancement
Task Allocation for All-in-One Store
|  | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4
| Week | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Qi Xu | T1 | T2 | T4 |  | T5 |  | T6
| Yan Fung Yenny Hou | 0: T2; 2: T3; 4: T5; 6: T7
| Yee Hei Ng | 0: T2; 2: T4; 4: T5; 6: T6
| Yin Kwan Chan | 0: T2; 2: T3; 4: T5; 6: T7