## Task Allocation
Task No | Task Name | Estimated Days
T1 | Website Templates | 3
T2 | Product List & Details | 4
T3 | Customer Account | 4
T4 | Shopping Cart | 4
T5 | Price Comparison | 6
T6 | Payment Integration | 4
Task Allocation for All-in-One Store
|  |  | Sprint 1 | Sprint 2 | Sprint 3
|  | Week | 1 | 2 | 3
|  | Yan Fung Yenny Hou |  | T6 | T5
|  | Yin Kwan Chan | T2 |  | T5
|  | Qi Xu | T1 | T4
|  | Yee Hei Ng |  |  | T3