[](https://goo.gl/owQa7A)**SIMPLE BUSINESS CASE TEMPLATE**

**LOGO**

|  |  |  |  |
| --- | --- | --- | --- |
| **SUBMITTED TO** | AllInOne Company | **SUBMITTED BY** | SmartGoal Limited |
| **TO THE ATTENTION OF** | Terry Chen | **POINT OF CONTACT** | Jennifer Li |
| **ADDRESS** | 199 West 49th Avenue  Vancouver B.C.  Canada V5Y 2Z6 | **ADDRESS** | 200 East 99th Avenue  Richmond B.C.  Canada V6A 888 |
| **PHONE** | 604.323.5511 | **PHONE** | 604.888.8888 |
| **EMAIL** | terry.chen@allinonestore.ca | **EMAIL** | jenniferli@smartgoal.ca |
| **DATE SUBMITTED** | 29th September 2022 | **DELIVERY METHOD** | Mail |

|  |
| --- |
| **REASON FOR THE PROJECT**  Describe why the project is needed, problems with the current situation, and why a change to the status quo is required. List the features, technology, equipment, benefits, and competitive advantages of this project. |
| AllinOne company is a trading company to sell various types of products. They currently only have a simple website showing a list of products. They receive customer orders by email or phone that require a lot of workforce and time to handle the requests. They would like a comprehensive website for customers to shop and place orders.  Desired Product Features:   1. Product searching and filtering 2. Order placing 3. Product price comparison from another website 4. Payment integration with various payment types   Benefits:   1. Provide one-day delivery service 2. Offer an efficient content management system 3. Enhance customer ordering experience   Technologies:   1. Use newer technology like React, JSFF, Bootstrap etc. 2. Adapt cloud services |
| **OPTIONS**  Describe briefly the different options for completing the solution. For example, to design a brochure, you could use templates from a word processing package, hire a designer, or design it yourself using clip art. |
| Three options to complete the solution:   1. Develop the website from scratch 2. Outsource the development to a vendor 3. Adapt existing e-commerce solution, e.g., WooCommerce / Shopify |
| **BENEFITS**  Describe anticipated improvements from the project. How can this project help the organization? For example, if we buy a license to a desktop publishing program, do we save on outsourcing our newsletter design? |
| This project can help the AllinOne company in below aspects:   1. Increase payment market share in the online shopping industry 2. Save resources on manual order processing and make more transactions and profits 3. Enhance marketing strategy by collecting Canadian market consumption data and building the data warehouse 4. Allow other organizations to promote and advertise on the new shopping site 5. Offer the opportunity to create the company’s profitable API |
| **COSTS**  How much will the project cost? Include contingency costs to cover overruns for risk events. Include ongoing maintenance and operational costs for the project. |
| * Human Resources:   + Salary : 20k per month (5k per person)     - Total: 60k (3 months)   + Insurance :     - General Liability: 75$ (3 months)     - Errors and Omissions 150$ (3 months)     - Cyber Liability: 450$ (3 months)     - Total: 675$   + Benefit :     - Red Pocket: 80$ (20$ per person) * Equipment / Services:   + Cloud service (for servers, database, hosting):     - Server: 1200$ (3 months)   + Hardware for developers:     - Desktop: 4k (1k per person)     - Monitor: 2k (500$ per person)   + Licensing (photoshop, team viewer):     - Photoshop: 60$ (20$ per month)     - Team viewer: 150$ (50$ per month)     - Copyrighting the project: 35$   + API cost: ~25$   + Domain name: 10$ (per year) * Contingency plan cost:   + Extra cloud service / hardware:     - Extra server: 1200$   + Extra staff:     - 60k * Total Cost: 129 435$ |
|  |
| Technology:   * Cloud service is unavailable or underperformance * API service is unavailable   Organizational:   * Change in management (requiring fewer developers)   People:   * Lack of developers due to virus outbreak   Requirements:   * Client changes all the requirement   Estimation:   * Scope of projects on payment gateway integration is underestimated   Tools:   * Software tools no longer supported   Legal:   * Legal issues on copyrights |
| **SCHEDULE**  Indicate how long the project will take, milestones, and how long before the benefits become apparent. Also, note if the time buffer is included in this estimate. |
| The project is planned to be completed in 6 months. Each sprint will take about one month:  1st Sprint   * Content management system (CMS)   + Backend UI system on product details   + User login logout   + Site settings * Service subscriptions (e.g. API)   2nd Sprint   * Front-end shopping cart   + Customer login logout   + Product listing   + Product filtering and searching   3rd Sprint   * Front-end shopping cart   + Price comparison   + Cart   + Order status tracking UI   4th Sprint   * Order management system   + Order request   + Order status   + Delivery process   5th Sprint   * Payment means integration * Web UI/UX enhancement   6th Sprint   * System test   + Full functional test and integration test   + Load & stress test * Hardware/software review * Buffer for ad-hoc requirements |
| **ASSESSMENT**  What are the costs of not doing the project? For example, will the newsletter be suspended indefinitely? What happens if the project isn’t undertaken? Can the organization afford the project? |
| Following cost will arise if not doing the project:   1. High human resource costs and processing time on handling orders 2. Less profits due to outdated website and less order handling ability 3. Less opportunity to increase the market share in the industry |
| **RECOMMENDATION**  Sum up and recommend why the project is a good idea. |
| The sudden appearance of the pandemic has seemingly changed the aspect of how customers interact with their regular businesses. With the option of physically walking into the store made impossible, everything was forced to go online. The trend of e-commerce has suddenly become clear, and now almost all well-known businesses have a website of their own. Creating a website with the bare minimum functions can be easily made, but what we need at this point of the cycle is look, feel, and uniqueness. Something we have and others don’t. Our project, “AllinOne website,” selects the best qualities from other websites in the current market and combines those components into one website. Our website provides a subscription to secure customer loyalty, price comparison to express our commitment, and a range of payment methods for the diverse population. All of these are planned to increase the company’s popularity and market share. |

|  |
| --- |
| **DISCLAIMER**  Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk. |